## Product Backlog
User Story ID | Title | Item Type | Assignee | Sprints | Story Points Estimate | Status | Remarks
| Staff - Job Roles | [6 empty] | Sprint Dates
US #1 | Staff views all job roles | User Story | Lee Wan Ning, Group Member C | Sprint 5 | 3 | done |  | Sprint 0 | 12 - 18 Sept
[8 empty] | Sprint 1 | 19 - 25 Sept
| Staff - Skills | [6 empty] | Sprint 2 | 26 - 2 Oct
US #2 | Staff views skills for a job role | User Story | Group Member B | Sprint 5 | 2 | done |  | Sprint 3 | 3 - 9 Oct
[8 empty] | Sprint 4 | 10 -16 Oct
| Staff - Courses | [6 empty] | Sprint 5 | 17 - 23 Oct
US #3 | Staff views courses related to skills | User Story | Group Member B | Sprint 5 | 8 | done |  | Sprint 6 | 24 - 30 Oct
[8 empty] | Sprint 7 | 31 - 6 Nov
Staff - Learning Journey
US #4 | Staff adds course to learning journey | User Story | Group Member C, Lee Wan Ning | Sprint 3 | 3 | done
US #5 | Staff views learning journey(s) | User Story | Group Member C, Group Member E , Group Member K | Sprint 4, Sprint 5 | 13 | done
US #6 | Staff removes course from learning journey | User Story | Group Member E , Group Member K | Sprint 6, Sprint 7 | 5 | done
US #18 | Staff Hard Deletes Learning Journey | User Story | Group Member E | Sprint 7 | 5 | done
HR - Job Roles
US #7 | HR creates job roles | User Story | Group Member K, Group Member B | Sprint 1, Sprint 2 | 1 | done
US #8 | HR views existing job role | User Story | Group Member E , Group Member X | Sprint 3 | 1 | done
US #10 | HR soft deletes job role | User Story | Group Member E | Sprint 3 | 3 | done
US #9 | HR updates existing job role | User Story | Group Member B | Sprint 4 | 2 | done
HR - Skills
US #11 | HR creates new skills | User Story | Group Member K, Group Member C | Sprint 1, Sprint 2 | 1 | done
US #12 | HR views existing skills | User Story | Group Member X, Group Member E | Sprint 2, Sprint 3 | 1 | done
US #13 | HR updates skills | User Story | Group Member C | Sprint 3 | 2 | done
US #14 | HR soft deletes existing skill | User Story | Group Member C | Sprint 3 | 3 | done
US #15 | HR assign skill to job role | User Story | Group Member B | Sprint 3, Sprint 4 | 5 | done
US #16 | HR assigns a skill to course | User Story | Group Member K | Sprint 3, Sprint 4 | 5 | done
Tasks
T #1 | UI Mockup/Design | Task | Group Member C | Sprint 0, Sprint 1 |  | done
T #2 | Find/Integrate a suitable template (react) | Task | Group Member C | Sprint 0, Sprint 1 |  | done
T #3 | Create Test Cases | Task | Everyone | Sprint 1, Sprint 4 |  | done
T #5 | Define Definition of Done document | Task | Group Member C | Sprint 1, Sprint 4, Sprint 5 |  | done
T #6 | Add Loading Icon (UI) | Task | Group Member C, Group Member B | Sprint 6, Sprint 7 |  | done
T #7 | Integration of new data given into current database | Task | Group Member X, Lee Wan Ning | Sprint 5, Sprint 6 |  | done
T #8 | Create unit test | Task | Group Member B, Group Member K, Group Member C | Sprint 6 |  | done
T #9 | Create API Documentation | Task | Group Member C, Group Member E | Sprint 6 |  | done
T #10 | Change staff ID from integer to string format in db | Task | Group Member X, Lee Wan Ning | Sprint 6 |  | done
T #11 | UAT Testing | Task | Group Member B, Group Member C, Lee Wan Ning, Group Member E | Sprint 5, Sprint 7 |  | done
T #12 | Rebase from dev to main (for sprint 6) | Task | Group Member B | Sprint 7 |  | done
T #13 | Epic Creation for future releases | Task | Group Member C, Group Member X | Sprint 7 |  | done
T #14 | Continuous Integration | Task | Group Member K, Group Member B | Sprint 6, Sprint 7 |  | done
T #15 | C4 Diagrams | Task | Group Member C, Group Member E | Sprint 0, Sprint 4, Sprint 5, Sprint 7 |  | done
T #16 | Demo Login Page Edits | Task | Lee Wan Ning, Group Member X | Sprint 6, Sprint 7 |  | done
T #17 | Workflow Diagram | Task | Group Member E | Sprint 0 |  | done
T #18 | Entity Relationship Diagram | Task | Group Member E | Sprint 0 |  | done
T #19 | Database setup | Task | Group Member X | Sprint 0 |  | done
Miscellaneous
US #17 | Staff Searches for Job Role | User Story |  |  | 8 | backlog
US #19 | Staff cannot add courses to their learning journey when pre-requisites are not met | User Story |  |  | 13 | backlog
Bug Fixes
BF #1 | Bug Fix: US#5 View Learning Journey | Bug Fix | Group Member K | Sprint 6 |  | done
BF #2 | Bug Fix: US#1 View Roles table | Bug Fix | Group Member C | Sprint 6 |  | done
Epics
E #1 | Manager views assigned team members | Epic |  |  | 21 | backlog
E #2 | Manager has unique access to specific features within LJPS | Epic |  |  | 21 | backlog
E #3 | Login to LJPS | Epic |  |  | 21 | backlog
E #4 | Staff automatically redirected to LMS after clicking on button on LJPS | Epic |  |  | 21 | backlog
E #5 | Auto Data Migration - Skills table fetched from LMS. | Epic |  |  | 21 | backlog