## Burnup
Burnup Chart
Date | Sprint 1 (19/09- 25/09) | Sprint 2 (26/09 - 02/10) | Sprint 3 (03/10 - 09/10) | Sprint 4 (10/10 - 16/10) | Sprint 5 (17/10 - 23/10) | Sprint 6 (24/10 - 30/10) | Sprint 7 (31/10 - 6/11)
Total Points | 65 | 65 | 65 | 65 | 71 | 71 | 71
Completed Points | 0 | 2 | 18 | 30 | 53 | 53 | 63

## Burndown
Overall Burndown Charts (Sprints 1-7)
Sprint | Total Planned Story Points | Actual Story Points Completed
Sprint 1 | 4 | 0
Sprint 2 | 3 | 2
Sprint 3 | 23 | 16
Sprint 4 | 25 | 12
Sprint 5 | 23 | 23
Sprint 6 | 5 | 0
Sprint 7 | 10 | 10
Average Velocity | 13.2857 | 9
Sprint 1
| Planned | Actual
2022-09-19 | 4 | 4
2022-09-20 | 3.3333 | 4
2022-09-21 | 2.6667 | 4
2022-09-22 | 2 | 4
2022-09-23 | 1.3333 | 4
2022-09-24 | 0.66667 | 4
2022-09-25 | 0 | 4
Sprint 2
| Planned | Actual
2022-09-26 | 3 | 3
2022-09-27 | 2.5 | 3
2022-09-28 | 2 | 3
2022-09-29 | 1.5 | 3
2022-09-30 | 1 | 3
2022-10-01 | 0.5 | 3
2022-10-02 | 0 | 1
Sprint 3
| Planned | Actual
2022-10-03 | 23 | 23
2022-10-04 | 19.1667 | 23
2022-10-05 | 15.3333 | 23
2022-10-06 | 11.5 | 14
2022-10-07 | 7.6667 | 14
2022-10-08 | 3.8333 | 5
2022-10-09 | 0 | 5
Sprint 4
| Planned | Actual
2022-10-10 | 25 | 25
2022-10-11 | 20.8333 | 25
2022-10-12 | 16.6667 | 15
2022-10-13 | 12.5 | 15
2022-10-14 | 8.3333 | 15
2022-10-15 | 4.1667 | 13
2022-10-16 | 0 | 13
Sprint 5
| Planned | Actual
2022-10-17 | 23 | 23
2022-10-18 | 19.1667 | 21
2022-10-19 | 15.3333 | 21
2022-10-20 | 11.5 | 10
2022-10-21 | 7.6667 | 10
2022-10-22 | 3.8333 | 0
2022-10-23 | 0 | 0
Sprint 6
| Planned | Actual
2022-10-24 | 5 | 5
2022-10-25 | 4.1667 | 5
2022-10-26 | 3.3333 | 5
2022-10-27 | 2.5 | 5
2022-10-28 | 1.6667 | 5
2022-10-29 | 0.83333 | 5
2022-10-30 | 0 | 5
Sprint 7
| Planned | Actual
2022-10-31 | 10 | 10
2022-11-01 | 8.3333 | 5
2022-11-02 | 6.6667 | 5
2022-11-03 | 5 | 5
2022-11-04 | 3.3333 | 0
2022-11-05 | 1.6667 | 0
2022-11-06 | 0 | 0
Sprint 1:
> Overestimated ability to delivery when the app is to be built with React.js, a language we weren’t familiar with before
> Also, more time went into setting up and configuration during initial stages
of development
Sprint 2:
> Development team getting used to the frameworks (React)
Sprint 3:
> More story points planned as the team gets more comfortable with the frameworks & sprint 3 was during recess week
> Velocity picked up to over 15 as the team could work for longer hours over the week as they were more available during recess week
Sprint 4:
> Story points completely remained relatively high at 12 as developers were more used to the react framework
Sprint 5:
> A high user story point story (view learning journey) that carried over from the previous week was completed this week.
> Caused a huge spike in velocity.
Sprint 6:
> Team focused mainly on building CI, testing pipelines, bug fixes and documentations for the impending release.
> The user story assigned for the week could not be considered as done as it failed integration tests.
Sprint 7:
> Most user stories for the 5 core features in release 1 are completed thus in the drop in user story points assigned per week.
> More time spent on rigorous testing via integration, UAT, regression & unit testing and fixing bugs that are identified from these testing means